## Stakeholder Matrix
Stakeholder | Role | Interest or requirement | Influence | Interest | Engagement approach | Evidence status
Sarah Ayvazyan | Patient | Simple online booking, timely cancellation and delay notices, clear next steps | Low | High | Keep informed | Supplied profile
Lak Ayer | Patient | Assisted/in-person booking and reachable prescription support | Low | High | Keep informed | Supplied profile
Dr. Aftab Khan | Cardiologist | Balanced schedules, diagnostic access, timely lab results and transfers | High | High | Manage closely | Supplied profile
Dr. Robert Lee | Orthopedist | Operating-room and equipment access, referral clarity, physiotherapy updates | High | High | Manage closely | Supplied profile
Santa Murmu | Pediatric nurse | Shift capacity, supplies and transfer notification | High | High | Manage closely | Supplied profile
Jessica Gomes | Emergency nurse | Weekend staffing, bed/monitor access, diagnostic results and ICU handoffs | High | High | Manage closely | Supplied profile
Maria Carter | Appointment scheduler | Conflict prevention, live availability and easier record retrieval | High | High | Manage closely | Supplied profile
Ivan Walker | Billing administrator | Complete scheduling and treatment data for reconciliation | High | High | Manage closely | Supplied profile
Rajesh Singh | IT manager | Integrated systems, network resilience and scalable architecture | High | Low | Keep satisfied | Supplied profile
Laura Simkow | Software developer | Usable interface, security remediation, notifications and analytics | High | Low | Keep satisfied | Supplied profile
Hospital leadership | Inferred governance stakeholder | Service performance, risk, scope and benefit decisions | High | High | Manage closely | Inferred governance role