## Detailed WBS
WBS ID | Work package / phase | Proposed owner | Predecessor | Milestone or output | Level
1.0 | Initiation and baseline | Project sponsor | — | Project charter and decision rights | Phase
1.1 | Confirm problem statement and intended outcomes | Business analyst | 1.0 | Problem statement reviewed | Work package
1.2 | Confirm governance, roles and decision routes | Project manager | 1.0 | Governance baseline | Work package
2.0 | Requirements and stakeholders | Business analyst | 1.0 | Requirements baseline | Phase
2.1 | Review profiles and operational datasets | Business analyst | 1.1 | Evidence inventory | Work package
2.2 | Document BRD and open questions | Business analyst | 2.1 | BRD review | Work package
2.3 | Build and reconcile RTM | Business analyst | 2.2 | RTM review | Work package
2.4 | Complete stakeholder analysis and engagement plan | Business analyst | 2.1 | Engagement plan review | Work package
3.0 | Process analysis and design | Business analyst | 2.0 | Workflow design baseline | Phase
3.1 | Model appointment As-Is and To-Be | Business analyst; scheduling | 2.3 | Workflow review | Work package
3.2 | Model check-in As-Is and To-Be | Business analyst; front desk | 2.3 | Workflow review | Work package
3.3 | Model interdepartmental communication | Business analyst; IT | 2.3 | Workflow review | Work package
3.4 | Build appointment, check-in and discharge swimlanes | Business analyst; clinical leads | 3.1–3.3 | Role/handoff review | Work package
4.0 | Data preparation and analysis | Data analyst | 2.1 | Analysis baseline | Phase
4.1 | Preserve and profile raw sources | Data analyst | 2.1 | Source control totals | Work package
4.2 | Clean duplicates, dates, missing values and categories | Data analyst | 4.1 | Clean datasets | Work package
4.3 | Validate keys, joins, cardinality and unmatched rows | Data analyst | 4.2 | Quality log | Work package
4.4 | Build patient feedback summary and appointment lookup | Data analyst | 4.3 | Combined analysis | Work package
4.5 | Create native PivotTables, charts and slicers | Data analyst | 4.4 | Analytical workbook | Work package
4.6 | Build and validate dashboard | Data analyst; operations | 4.5 | Dashboard review | Work package
5.0 | Risk and controls | Business analyst; risk owners | 2.0–4.0 | Risk baseline | Phase
5.1 | Create risk register and SWOT | Business analyst | 3.0;4.0 | Risk review | Work package
5.2 | Prioritize risks and define mitigation | Risk owners | 5.1 | Mitigation review | Work package
5.3 | Define contingencies, triggers and monitoring | Risk owners | 5.2 | Continuity review | Work package
6.0 | Pilot preparation and validation | Project team | 3.0–5.0 | Go/no-go evidence | Phase
6.1 | Configure pilot workflows and controls | IT; operations | 3.0;5.0 | Pilot ready | Work package
6.2 | Prepare role-based training and support | Change lead | 6.1 | Training ready | Work package
6.3 | Execute planned UAT and reconcile RTM | UAT lead; stakeholders | 6.1 | UAT decision | Work package
6.4 | Review security, downtime and data-quality gates | IT; security; data owner | 6.1 | Control decision | Work package
7.0 | Operate and review | Operations; sponsor | 6.0 | Pilot review | Phase
7.1 | Monitor agreed KPIs, adoption, exceptions and risks | Operations; data owner | 6.3 | 30-day review | Work package
7.2 | Decide scale, revise, pause or rollback | Sponsor; governance group | 7.1 | Decision recorded | Work package