# HealthFirst Care Risk Matrix and Mitigation Plan

Capstone Project M05L02

Adwoa Boama Acheampong  |  IBM Business Analyst learning project

# Priority and planning basis

R01 and R02 have the maximum initial score of 9. R04, R06 and R07 score 6 and are also High on the 3 × 3 planning matrix. These five high-priority risks require prevention, trigger, owner and contingency; the remaining five are monitored with the same fields. No residual reduction is claimed until controls are tested and owners rescore each risk.

# Updated 3 × 3 priority matrix

Initial positions are shared with the risk register. After evidence-based mitigation, owners update likelihood and impact in the workbook; the matrix recalculates from those inputs.

| ID | Preventive action | Owner | Trigger | Contingency | Residual target | Review |
| --- | --- | --- | --- | --- | --- | --- |
| R01 | Conflict rules, scenario UAT and daily exception review | Operations manager | Double booking or override trend | Pause affected scheduling path; use controlled manual calendar and reconcile later. | Unscored; review after test | Daily during pilot |
| R02 | Field mapping, reconciliation, retry queue, monitoring and rollback | IT manager | Stale sync or reconciliation variance | Disable failing interface; use validated batch extract and preserve exception log. | Unscored; review after test | Daily during pilot |
| R03 | Department thresholds, protected capacity and escalation | Clinical operations | Wait or utilisation threshold breach | Rebalance slots/resources or invoke approved surge, transfer or reschedule rules. | Unscored; review after test | At each stage gate |
| R04 | Least privilege, MFA, audit logging, encryption and incident exercises | Security lead | Unauthorized access or delivery exposure | Contain access, preserve evidence and invoke the approved privacy incident process. | Unscored; review after test | Daily during pilot |
| R05 | Co-design, role training, floor support and usage review | Change lead | Bypass or duplicate-entry trend | Remove unsafe parallel process, deploy champions and target retraining. | Unscored; review after test | At each stage gate |
| R06 | Validation rules, exception queue, ownership and quality scorecard | Data owner | Missing or duplicate keys rise | Qualify affected KPI, quarantine suspect rows and correct the source before decision use. | Unscored; review after test | Daily during pilot |
| R07 | Downtime procedure, monitoring and reconciliation drills | IT incident lead | Connectivity or service outage | Use the approved downtime list and reconcile every record after restoration. | Unscored; review after test | Daily during pilot |
| R08 | Accessibility review, assisted booking and usability testing | Patient experience lead | Abandonment or support complaints | Switch to assisted booking or check-in and correct inaccessible content. | Unscored; review after test | At each stage gate |
| R09 | Metric dictionary, denominator review and formal baseline approval | Project sponsor | Conflicting dashboard interpretations | Suspend the disputed KPI from decision use until definition and baseline are approved. | Unscored; review after test | At each stage gate |
| R10 | Scope baseline, change assessment and sponsor decision | Project manager | Unplanned deliverable or dependency | Stop unapproved work and route the change through sponsor review. | Unscored; review after test | At each stage gate |

# Escalation and continuity

| Event | Immediate action | Continuity method | Decision owner |
| --- | --- | --- | --- |
| Scheduling or HIS outage | Declare incident and preserve current queue | Controlled downtime list with reconciliation | IT incident lead |
| Incorrect or missing feed | Quarantine affected dashboard data | Show freshness warning and use validated prior extract | Data owner |
| Notification failure or exposure | Stop repeated sends and assess recipients | Phone high-risk changes using minimum necessary data | Operations and security |
| Capacity threshold breach | Escalate and reassess appointments | Approved overflow, transfer or reschedule rule | Clinical lead |
| Critical security event | Revoke access, contain and preserve evidence | Approved minimum-data manual process | Security lead |

# Acceptance evidence

Control owner is named and accepts responsibility.

Trigger can be observed from an agreed source.

Preventive control passes its planned test.

Contingency is exercised or walkthrough evidence is retained.

Residual score and any remaining limitation are reviewed by the sponsor.

# Conclusion

The mitigation plan is complete as a planning artifact. It does not claim that controls have been implemented, tested or accepted. Those statuses remain open in the RTM and risk register until evidence is added.