## Risk Register
ID | Cause event and consequence | Category | Likelihood | Impact | Score | Rating | Owner | Existing or planned controls | Trigger | Response strategy | Status | Dependencies | Review cadence
R01 | Configuration fails to prevent scheduling conflicts, so double bookings continue and patients are delayed. | Operational | 3 | 3 | 9 | High | Operations manager | Conflict rules; scenario UAT; daily exceptions | Double booking or override trend | Pause affected path; use controlled manual calendar and reconcile later. | Open - planning | Control owner; pilot design; evidence retention | Daily during pilot
R02 | Legacy interfaces fail or lag, creating incomplete records and unreliable decisions. | Technical/data | 3 | 3 | 9 | High | IT manager | Mapping; reconciliation; retry queue; rollback | Stale sync or reconciliation variance | Disable failing interface; use validated batch extract. | Open - planning | Control owner; pilot design; evidence retention | Daily during pilot
R03 | Demand exceeds capacity, shifting rather than removing bottlenecks. | Capacity | 2 | 2 | 4 | Medium | Clinical operations | Capacity thresholds; protected slots; escalation | Wait or utilisation threshold breach | Rebalance resources or invoke approved surge/transfer rule. | Open - planning | Control owner; pilot design; evidence retention | Daily during pilot
R04 | Weak access or notification controls expose patient information. | Security | 2 | 3 | 6 | High | Security lead | Least privilege; MFA; audit; encryption | Unauthorized access or delivery exposure | Contain access; preserve evidence; invoke privacy incident process. | Open - planning | Control owner; pilot design; evidence retention | Daily during pilot
R05 | Staff bypass workflows, causing duplicate entry and inconsistent records. | Adoption | 2 | 2 | 4 | Medium | Change lead | Co-design; training; floor support; usage review | Bypass or duplicate-entry trend | Deploy champions and targeted retraining; remove unsafe parallel path. | Open - planning | Control owner; pilot design; evidence retention | Weekly
R06 | Missing or mismatched source data distorts dashboard decisions. | Data quality | 3 | 2 | 6 | High | Data owner | Validation; exception queue; quality scorecard | Missing or duplicate keys rise | Quarantine affected data; qualify KPI and correct source. | Open - planning | Control owner; pilot design; evidence retention | Weekly
R07 | Network downtime interrupts booking, check-in or notices. | Continuity | 2 | 3 | 6 | High | IT incident lead | Downtime procedure; monitoring; reconciliation drills | Connectivity or service outage | Use approved downtime list; reconcile after restoration. | Open - planning | Control owner; pilot design; evidence retention | Daily during pilot
R08 | Self-service design excludes patients who need assisted access. | Stakeholder/access | 2 | 2 | 4 | Medium | Patient experience lead | Accessibility review; assisted booking; usability tests | Abandonment or support complaints | Switch to assisted route and correct inaccessible content. | Open - planning | Control owner; pilot design; evidence retention | At stage gate
R09 | Undefined KPI thresholds lead to misleading performance judgments. | Governance | 2 | 2 | 4 | Medium | Project sponsor | Metric dictionary; denominator review; baseline approval | Conflicting dashboard interpretations | Suspend disputed KPI until definition is approved. | Open - planning | Control owner; pilot design; evidence retention | Weekly
R10 | Scope expands into clinical decisions or full platform replacement, delaying pilot. | Scope | 1 | 2 | 2 | Low | Project manager | Scope baseline; change assessment; sponsor decision | Unplanned deliverable or dependency | Stop unapproved work; route change to sponsor. | Open - planning | Control owner; pilot design; evidence retention | Weekly

## Risk Matrix
HealthFirst Care ¦ 3 × 3 likelihood-impact matrix
Likelihood ↓ / Impact → | 1 | 2 | 3
3 |  | R06 | R01, R02
2 |  | R03, R05, R08, R09 | R04, R07
1 |  | R10
Low: 1–2; Medium: 3–4; High: 6–9. Scores are planning judgments.
Cells list IDs dynamically from the local Risk Register.

## SWOT & Mitigation
Strengths | Weaknesses | Opportunities | Threats
Appointment, feedback and resource data already exist | Disconnected systems and incomplete records | Shared capacity visibility can reduce conflicts | Security failure could expose patient information
Stakeholders identify concrete workflow pain points | Weak completion, no-show and wait indicators | Notifications can improve attendance and confidence | Poor adoption may preserve parallel workflows
Operational objectives and provisional targets are defined | Department-only common analytical key | Governed dashboards can support local decisions | Peak demand may shift delays between departments
Phased pilot limits implementation exposure | Legacy integration and network constraints | Exception data can drive iterative improvement | Unvalidated targets may distort performance decisions
Risk | Preventive control | Trigger | Contingency | Owner | Review point
R01 | Conflict rules; scenario UAT; daily exceptions | Double booking or override trend | Pause affected path; use controlled manual calendar and reconcile later. | Operations manager | Daily during pilot
R02 | Mapping; reconciliation; retry queue; rollback | Stale sync or reconciliation variance | Disable failing interface; use validated batch extract. | IT manager | Daily during pilot
R03 | Capacity thresholds; protected slots; escalation | Wait or utilisation threshold breach | Rebalance resources or invoke approved surge/transfer rule. | Clinical operations | At each stage gate
R04 | Least privilege; MFA; audit; encryption | Unauthorized access or delivery exposure | Contain access; preserve evidence; invoke privacy incident process. | Security lead | Daily during pilot
R05 | Co-design; training; floor support; usage review | Bypass or duplicate-entry trend | Deploy champions and targeted retraining; remove unsafe parallel path. | Change lead | At each stage gate
R06 | Validation; exception queue; quality scorecard | Missing or duplicate keys rise | Quarantine affected data; qualify KPI and correct source. | Data owner | Daily during pilot
R07 | Downtime procedure; monitoring; reconciliation drills | Connectivity or service outage | Use approved downtime list; reconcile after restoration. | IT incident lead | Daily during pilot
R08 | Accessibility review; assisted booking; usability tests | Abandonment or support complaints | Switch to assisted route and correct inaccessible content. | Patient experience lead | At each stage gate
R09 | Metric dictionary; denominator review; baseline approval | Conflicting dashboard interpretations | Suspend disputed KPI until definition is approved. | Project sponsor | At each stage gate
R10 | Scope baseline; change assessment; sponsor decision | Unplanned deliverable or dependency | Stop unapproved work; route change to sponsor. | Project manager | At each stage gate